## Sheet1
Big Boss's Schedule
Progression so far
Progression goal
Project Timeline | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
Development
Script Writing
Cassandra M. | bar: Week 1 to Week 5
John L. | bar: Week 1 to Week 5
Financing
Trystyn R. | bar: Week 1 to Week 10
Pre-Production
Character Concepts
Cassandra M. | bar: Week 2 to Week 6
Dylan R. | bar: Week 1 to Week 6
Liam N. | bar: Week 2 to Week 6
Weapons design/concepts
Gawain I. | bar: Week 1 to Week 4
Jerry H. | bar: Week 1 to Week 4
Logo design
Peter P. | bar: Week 3
Production
2D Modelling/ Rendering
Dylan R. | bar: Week 6 to Week 10
Gawain I. | bar: Week 6 to Week 10
Level Design
Cassandra M. | bar: Week 6 to Week 11
Nancy Z. | bar: Week 6 to Week 11
Clark K. | bar: Week 6 to Week 11
Sound Production
Liam N. | bar: Week 8 to Week 12
Nick S. | bar: Week 8 to Week 12
Play Testing
Guest 1 | bar: Week 13 to Week 14
Guest 2 | bar: Week 13 to Week 14
Guest 3 | bar: Week 13 to Week 14
Guest 4 | Guest 5 | Guest 6 | Guest 7 | Guest 8 | Guest 9 | Guest 10 | Guest 11 | Guest 12 | Guest 13 | Guest 14 | Guest 15 | Guest 16 | Guest 17
Post- Production
Level Editing
Cassandra M.
Nancy Z.
Clark K.
Finalizing
Dylan R.
Gawain I.
Nick S.